## Sheet1
Stand-up questions | Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6
| 10/8/2021 - 10/15/2021 | 10/16/2021 - 10/22/2021 | 10/22/2021 - 10/28/2021 | 10/28/2021 - 11/04/2021 | 11/04/2021-11/11/2021 | 11/11/2021-11/18/2021
ISHA
What tasks did I work on / complete? | Understanding the project requirements Designing UI wireframes screens for flight booking functionality | Devloped UI wireframes for my trips and cancel/update flight screen, developed UI for home page of airline website | developed the front end for flight booking screen | developing the flight listing screen for the website, frontend/backend | displaying flight results based on number of travellers,displaying amount in money/miles | Developing trip summary screen, traveller information screen
What am I planning to work on next? | develop the home page for airline system | developing functionalities for airline | developing the flight listing screen for the website | adding validations and displaying data based on selection of inputs for flight list screen | starting with the development of flight summary screen | developing a dummy payment gateway screen
What tasks are blocked waiting on another team member? | NA | NA | NA | NA | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | we discussed our task progress in the daily meeting and solved any blockers we faced together (XP value: communication)
HIMAKSHI
What tasks did I work on / complete? | Determining entities,attributes along with the relationship | Understanding flow of mileage plus account, DB Design and table creation, mock data for all tables and UI wireframe for login and traveller details page | Developed Booking history page frontend and backend | Developed Cancel booking option frontend | Developed Edit Reservation Page | Developed Admin Page with Edit Flight and Add New Flight Option
What am I planning to work on next? | Table creation and DB design,mock data for all tables | Booking history pages | Developing Cancel booking option | Developing Cancel and Edit booking option frontend and backend | Developing Admin Home page with Edit Flight Details | Implementing Required Validations on Add Flight and Update Flight Page
What tasks are blocked waiting on another team member? | NA | NA | NA | NA | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Through regular meetings, everyone discussed functionalities in details which help us achieved the well reviewed solution.
JAHNAVI
What tasks did I work on / complete? | Architecture diagram ,UI wireframe for customer signup and Home | Design and creation of tables namely Booking, Seat, FlightSeat, Traveller in DB and review with the team. Created UI wireframe for Mileage details page | Designed and implemented Login and signup pages on frontend | Integrated signup and login on backend. Created and maintained session upon login. Also integrated with logout. | Developed Mileage rewards account page on both frontend and backend. | partial implementation of booking details page.
What am I planning to work on next? | DB design | Signin and Signup pages | Integrated signup and login on backend. | Creation of page for mileage rewards account | Display booking details summary and book a ticket. | Integrate frontend and backend for booking details summary and book a ticket.
What tasks are blocked waiting on another team member? | NA | NA | NA | NA | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Communication - Discussion about technology stack and requirements | Communication - Discussed about the design decisions with the team and got it reviewed. | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation | Communication - Effectively communicated with the team related toapproach and implementation
ANIL
What tasks did I work on / complete? | Project setup & boilerplate code | Integrated mysql , sign in page mock. | Created basic seat map with seat numbers | Implemented cost of seats | Added seat UI modifications | Add flight data
What am I planning to work on next? | Integrate Mysql & mock login page | Design Seat booking UI | Seat Cost based on position | Enhance seat UI & fix bugs | Add Flight details | Merge backend and frontend for seat
What tasks are blocked waiting on another team member? | NA | None | NA | NA | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Respect - others choice of design | Communication - DB design discussions. | Communication - discussed seat map design for seat selection