## Sheet1
Stand-up questions | Week #1 | Week #2
| 10/8/2021 - 10/15/2021 | 10/16/2021 - 10/22/2021
ISHA
What tasks did I work on / complete? | Understanding the project requirements Designing UI wireframes screens for flight booking functionality | Devloped UI wireframes for my trips and cancel/update flight screen, developed UI for home page of airline website
What am I planning to work on next? | develop the home page for airline system | developing functionalities for airline
What tasks are blocked waiting on another team member? | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | we discussed our task progress in the daily meeting and solved any blockers we faced together
HIMAKSHI
What tasks did I work on / complete? | Determining entities,attributes along with the relationship | Understanding flow of mileage plus account, DB Design and table creation, mock data for all tables and UI wireframe for login and traveller details page
What am I planning to work on next? | Table creation and DB design,mock data for all tables
What tasks are blocked waiting on another team member? | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Through regular meetings, everyone received constant constructive feedback which help us achieved the well reviewed solution
JAHNAVI
What tasks did I work on / complete? | Architecture diagram ,UI wireframe for customer signup and Home | Design and creation of tables namely Booking, Seat, FlightSeat, Traveller in DB and review with the team. Created UI wireframe for Mileage details page
What am I planning to work on next? | DB design
What tasks are blocked waiting on another team member? | NA | NA
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Communication - Discussion about technology stack and requirements | Communication, feedback -Discussed about the design decisions with the team and got it reviewed.
ANIL
What tasks did I work on / complete? | Project setup & boilerplate code | Integrated mysql , sign in page mock.
What am I planning to work on next? | Integrate Mysql & mock login page
What tasks are blocked waiting on another team member? | NA | None
Select one of the XP Core Values and keep a journal of how the team kept these values throughout the project. | Respect - others choice of design | Communication - DB design discussions.