## Sheet1
|  |  |  | Week #1 (7 hrs / week) | [6 empty] | Week #2 (7 hrs / week) | [6 empty] | Week #3 (7 hrs / week) | [6 empty] | Week #4 (7 hrs / week) | [5 empty] | Week #4 ( hrs / week) | [6 empty] | Week #6 (10 hrs / week) | [5 empty] | Week #7 (10 hrs / week) | [6 empty] | Week #8 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 28 x 8) = 224 | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27
|  |  |  | 2021-10-07 | [11 empty] | 2014-09-25 | 2014-09-26 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09
224
|  |  | 216 | 8 | 6 | 5 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0
Understanding the Project Requirements | Understanding User interfaces for airline reservation system on high level
| Understanding existing Airline interface |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| understanding the functionalities for various features of airline system | Anil Gubbala | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| Identifying entities and relationship between them to build the database structure | Himakshi
Project setup & Boiler plate code for further implementations | Create React app & Node js server | Anil Gubbala | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0
| Connect frontend and backend | Anil Gubbala | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
Create initial wireframes | Create Wireframe for Customer signup page | Jahnavi Marthala | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Create Wireframe for Home page | Jahnavi Marthala | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Creating UI design for flight booking Screen | Isha Rao | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0
| Creating wireframe for seat selection screen | Isha Rao | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
Create initial architecture diagram | Architecture diagram for technology stack | Jahnavi Marthala | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
Manage your Mileage rewards account |  |  | 28
Search for flights and book travel |  |  | 28
Change/Cancel reservations |  |  | 28
Enrolling as a new customer |  |  | 28
Purchase seats |  |  | 28
Deployment & Documentation |  |  | 28
Integration of each other task |  |  | 28
Team:
Isha | 7 hours / Week
Himakshi | 7 hours / Week
Jahnavi | 7 hours / Week
Anil | 7 hours / Week
Total Available Hours During Sprint: